## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-05-06 | Done | Kick of lecture | Kick of lecture about block D | Lecture | ILO 1.3 | 4 | 4 | 0
2025-05-06 | Done | Datacamp | Datacamp Introduction to SQL | Study | ILO 6.2 | 1 | 1 | 0
2025-05-06 | Done | Data lab | Reading data lab task | Study | ILO 6.2 | 4 | 3 | -1 | Reading data lab content and trying to undrestand better stock market through watching some youtube video.
2025-02-07 | Done | Data lab | Reading a datalab content | Study |  | 2 | 2 | 0 | Getting information about Data warehouse and scheme design.
2025-05-07 | Done | Data camp | Data Warehouse basics course from Datacamp | Study | ILO 6.2 | 3 | 3 | 0 | Getting information about difference of database and data warehouse.
2025-05-07 | Done | Datacamp course | Datacamp course about sql | Study | ILO 6.2 | 3 | 3 | 0 | About SQL and how to manage the data in sql
2025-05-08 | Done | Datalab task | SQL upskilling | Study | ILO 6.2 | 2 | 2 | 0 | It was about database design
2025-05-08 | Done | Datalab task | practicing sql on datalab task | Programming | ILO 6.2 | 1 | 1 | 0 | practicing sql and learning new skill.
2025-05-09 | Done | SQL | practicing sql on datalab task | Programming | ILO 6.2 | 4 | 4 | 0 | Practicing sql which it was easy till level 3 but in level 4 I had some problem to solve it.
2025-05-10 | Done | Individual Idea | Data Warehouse | Research | ILO 6.2 | 4 | 4 | 0 | visiting data warehouse to be familiar with data
2025-05-10 | Done | Stockmarket | Stock market Nasdaq | Research | ILO 1.3 | 4 | 4 | 0 | watching some video to get familiar with stock and stock market
2025-05-11 | Done | Individual Idea | Working on my Individual Idea | Research | ILO 1.3 | 4 | 4 | 0 | Working to find some indiviual Idea
|  |  |  | Total Hours |  | 36 | 35 | -1
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2025-05-12 | Done | Time series | reading the datalab task and contents. | Study | ILO 1.3 | 3 | 3 | 0
2025-05-12 | Done | Busines model canvas | Reading data lab task | Study | ILO 1.3 | 2 | 2 | 0 | Getting familiar to how can I fill the business model canvas.
2025-05-12 | Done | Legal frame work | Trying to complete legal frame work template | Research | ILO 3.2 | 4 | 4.5 | 0.5
2025-05-13 | Done | Legal frame work | Trying to complete it and also check with Zhana | Evidencing | ILO 3.2 | 3 | 3 | 0 | Checking with Zhana and changing the refrences model.
2025-05-14 | Done | Visualising time series | Reading and practicing | Study | ILO 8.2 | 4 | 4 | 0 | Reading all the datalab content and also practicing them in VS code to learn it better.
2025-05-14 | Done | Datacamp course | Visulising time series data in python | Study | ILO 8.2 | 3 | 3.5 | 0.5
2025-05-15 | Done | Datacamp | Time series analysis in python | Study | ILO 8.2 | 4 | 4 | 0
2025-05-15 | Done | Datalab content | Arima modeling | Study | ILO 8.2 | 4 | 4 | 0
2025-05-16 | Done | Time series | Start working on Time series template | Programming | ILO 8.2 | 3 | 3 | 0
2025-05-16 | Done | Time series | Continue working on time series tempate | Programming | ILO 8.2 | 4 | 4 | 0
|  |  |  | Total Hours |  | 34 | 35 | 1
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-05-19 | Done | Time series template | Start practicing on time series template | Programming | ILO 8.2 | 3 | 3 | 0 | Start practicing time series part on template
2025-05-19 | Done | Individual Idea | Making busines model canvas | Research | ILO 4.1 | 4 | 4 | 0 | final search and tought about my final Indivudual idea
2025-05-20 | Done | Time series template | Start filling the time series template | Programming | ILO 8.2 | 3 | 3 | 0
2025-05-20 | Done | presentation | preparing for presenting the individual Idea | Study | ILO 4.1 | 2 | 2 | 0
2025-05-21 | Done | Data lab | Going through datalab content | Study | ILO 8.2 | 4 | 4 | 0
2025-05-21 | Done | Youtube video | Watching youtube video about RNN and LSTM | Study | ILO 8.2 | 3 | 3 | 0
2025-05-22 | Done | Datalab | Going through datalab content | Study | ILO 1.3 | 4 | 4 | 0
2025-05-23 | Done | Time series template | Start woorking on Machine learning part of Time series template | Programming | ILO 8.2 | 3 | 3 | 0
2025-05-24 | Done | Time series template | Start working on Time series template | Programming | ILO 8.2 | 4 | 4 | 0 | Implementing machine learning model on time series template
2025-05-25 | Done | Evidencing | Evidencing on worklog and learning log | Evidencing | ILO 1.3 | 2 | 2 | 0
|  |  |  | Total Hours |  | 32 | 32 | 0
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-05-26 | Done | Group Idea | Preparing our note about the finnal Group idea | Research | ILO 4.1 | 3 | 3 | 0
2025-05-27 | Done | Final team idea | Developing final team idea | Research | ILO 4.1 | 3 | 3 | 0
2025-05-27 | Done | GDPR template | Preparing the final GDPR for the final team Idea | Evidencing | ILO 4.1 | 4 | 4 | 0
2025-05-27 | Done | Data | working on dataware house and find a good dataset | Programming | ILO 4.1 | 2 | 2 | 0 | finding a good dataset or stock which it has a less missing values.
2025-05-28 | Done | Team work | Start working as a team find a good model for our project | Programming | ILO 8.2 | 2 | 2 | 0
2025-05-28 | Done | Team work | Starting EDA on our dataset and give some feedback | Programming | ILO 8.2 | 3 | 3 | 0 | To find a missing value and look at the chart to find out is a good dataset for our project or not yet
2025-05-29 | Done | Working on Legal risk | Working on Legal risk pdf and make it ready | Research | ILO 3.2 | 4 | 4 | 0
2025-05-29 | Done | SQL | making database for our project | Programming | ILO 8.2 | 2 | 2 | 0 | Giving feedback to our peers to change or ad something on it.
2025-05-30 | Done | Machine learning | implement different model of machine learning | Programming | ILO 8.2 | 4 | 4 | 0
2025-05-30 | Done | Datalab | Workshop | Workshop | ILO 4.1 | 4 | 4 | 0
|  |  |  | Total Hours |  | 31 | 31 | 0
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-06-02 | Done | EDA | Start doing EDA on our data source | Programming | ILO 9.1 | 3 | 3 | 0 | Starting doing EDA to see how is our dataset
2025-06-02 | Done | Machine learning | implement different model of machine learning | Programming | ILO 8.2 | 5 | 5 | 0
2025-06-03 | Done | Machine learning | implement different model of machine learning | Programming | ILO 8.2 | 5 | 5 | 0
2025-06-04 | Done | Machine learning | implement different model of machine learning | Programming | ILO 8.2 | 5 | 5 | 0
2025-06-05 | Done | Machine learning | implement different model of machine learning | Programming | ILO 8.2 | 5 | 5 | 0
2025-06-06 | Done | Machine learning | implement different model of machine learning | Programming | ILO 8.2 | 5 | 5 | 0 | For this week I tried to implement 3 model of machine learning and always changing some parameters to get a better accuracy and result.
2025-06-07 | Done | Research | Searching to find some other project same as our project to find out which model they trained. | Programming | ILO 9.1 | 4 | 4 | 0 | Searching to find other model of training and give some example t how they did this.
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 32 | 32 | 0
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-06-09 | Done | Hypermeter tuning | Gridsearch and feature extraction | Programming | ILO 9.1 | 5 | 5 | 0
2025-06-10 | Done | Hypermeter tuning | Gridsearch and feature extraction | Programming | ILO 9.1 | 4 | 4 | 0
2025-06-11 | Done | Class weigh | Trying to use Smote and compute class weight | Programming | ILO 8.2 | 4 | 4 | 0 | Trying to use Smote and compute class weight to balance our imbalance data
2025-06-11 | Done | GDPR template | review it and submit it | Research | ILO 4.1 | 2 | 2 | 0
2025-06-12 | Done | Machine learning | Changing target and feature | Programming | ILO 2.3 | 4 | 4 | 0 | checking the other way to find a target with using more feature
2025-06-13 | Done | Machine learning | Find the best model | Programming | ILO 8.2 | 4 | 4 | 0 | comparing and find a best model out of my models that I implement it.
2025-06-13 | Done | Machine learning | Implement NFT model | Programming | ILO 8.2 | 4 | 4 | 0 | I tried to test the nft model but unfortunately I didn't get a good result.
2025-06-14 | Done | Evidencing | Evidencing on worklog and learning log | Evidencing | ILO 1.3 | 3 | 3 | 0
2025-06-15 | Done | Peer feedback | Giving feedback to my peers | Evidencing | ILO 2.3 | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 31 | 31 | 0
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-06-16 | Done | SQL | Checking SQL practice work and make it ready for uploading | Evidencing | ILO 8.2 | 2 | 2 | 0
2025-06-16 | Done | Time series template | Checking time series template and make it ready to submit | Programming | ILO 8.2 | 2 | 2 | 0
2025-06-17 | Done | Hypermeter tuning | Checking the final Hypermeter tuning | Programming | ILO 8.2 | 1 | 1 | 0
2025-06-17 | Done | presentation | Making slides for the presentation | Evidencing | ILO 4.1 | 4 | 4 | 0
| Done | presentation | Making my oral script for presentation | Evidencing | ILO 4.1 | 2 | 2 | 0
2025-06-18 | Done | presentation | Changing samething in presentation and add more detail to it | Evidencing | ILO 2.3 | 4 | 4 | 0
2025-06-19 | Done | Evidencing | Evidencing on worklog and learning log | Evidencing | ILO 1.3 | 2 | 2 | 0
| Done | Evidencing | Making ready for submision | Evidencing | ILO 1.3 | 4 | 4 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 21 | 21 | 0
Total Hours
|  |  |  | Total hours this block |  | 217 | 217 | 0

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.3 | 12 | 5 | 6 | 0 | 0 | 3 | 6 | 0 | 32
ILO 2.3 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 9
ILO 3.2 | 0 | 7.5 | 0 | 4 | 0 | 0 | 0 | 0 | 11.5
ILO 4.1 | 0 | 0 | 6 | 16 | 0 | 2 | 6 | 0 | 30
ILO 6.2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
ILO 8.2 | 0 | 22.5 | 20 | 11 | 25 | 12 | 5 | 0 | 95.5
ILO 9.1 | 0 | 0 | 0 | 0 | 7 | 9 | 0 | 0 | 16
TOTAL HOURS PER WEEK | 33 | 35 | 32 | 31 | 32 | 31 | 21 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
If you add more rows to the Worklog Tasks and Time sheet, make sure to update the row count accordingly. For example, if you add an additional row for Week 1, you'll need to adjust all formula in Column C from H14 to H15 and F14 to F15 | bar: W1 to W4

## Drop-downs (hidden)
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.3
Unplanned | Meeting | ILO 2.3
Blocked | Programming | ILO 3.2
In-Progress | Research | ILO 4.1
Done | Testing | ILO 6.2
Delayed | Workshop | ILO 8.2
Cancelled | Planning | ILO 9.1
Evidencing
Debugging
Lecture
Study
Unplanned
Distraction
Break